## 4-Month Agentic AI Plan
Date | Day | BUILD Task (80%) | Learn Resource (20%) | Tools/Concepts | Done
🚀 MONTH 1: FOUNDATION + FIRST AGENT (January)
Week 1: Setup & First API Call
Jan 01 | Day 1 | Setup: API keys (Claude/OpenAI), install libraries | Watch: Anthropic API Quickstart (15 min) | API, Environment Setup | ☐
Jan 02 | Day 2 | Build: Simple chatbot CLI that calls Claude API | Read: API documentation basics | Python requests, JSON | ☐
Jan 03 | Day 3 | Build: Add conversation memory to your chatbot | Debug your code errors | Lists, File I/O | ☐
Jan 04 | Day 4 | Build: Make chatbot respond in different tones | Experiment with system prompts | Prompt Engineering | ☐
Jan 05 | Day 5 | Build: Add token counting & cost tracking | Learn: Token limits | tiktoken library | ☐
Jan 06 | Day 6 | Build: Create a joke generator bot with categories | Test edge cases | Error Handling | ☐
Jan 07 | Day 7 | Build: Multi-turn conversation with context | Read about conversation patterns | Context Management | ☐
Week 2: Web Search Agent
Jan 08 | Day 8 | Build: Script that searches Google (use SerpAPI) | Setup: Get SerpAPI free key | API Integration | ☐
Jan 09 | Day 9 | Build: Claude agent that decides when to search | Read: Tool use documentation | Function Calling | ☐
Jan 10 | Day 10 | Build: Add summarization to search results | Test with different queries | Text Processing | ☐
Jan 11 | Day 11 | Build: Multi-step research agent (search → analyze → report) | Learn: Chain of thought | Agent Patterns | ☐
Jan 12 | Day 12 | Build: Add source citations to responses | Practice prompt engineering | Structured Output | ☐
Jan 13 | Day 13 | Build: Create a news briefing generator | Refine your prompts | Automation | ☐
Jan 14 | Day 14 | MILESTONE: Research Agent v1.0 - Push to GitHub | Write README and demo video | Git, Documentation | ☐
Week 3: LangChain Basics
Jan 15 | Day 15 | Build: Convert your chatbot to use LangChain | Install: langchain, langchain-anthropic | LangChain Setup | ☐
Jan 16 | Day 16 | Build: Add memory using ConversationBufferMemory | Read: Memory types | LangChain Memory | ☐
Jan 17 | Day 17 | Build: Create a prompt template system | Learn: PromptTemplate class | Templates | ☐
Jan 18 | Day 18 | Build: Chain multiple LLM calls together | Read: LangChain chains | LCEL (LangChain Expression Language) | ☐
Jan 19 | Day 19 | Build: Add a calculator tool to your agent | Test math problems | LangChain Tools | ☐
Jan 20 | Day 20 | Build: Create a Wikipedia research agent | Add: WikipediaAPIWrapper | Tool Integration | ☐
Jan 21 | Day 21 | Build: Document Q&A over your own text files | Learn: Text splitting | Document Loaders | ☐
Week 4: Memory & Vector Databases
Jan 22 | Day 22 | Build: Install ChromaDB and create first collection | Read: What are embeddings? | Vector Databases | ☐
Jan 23 | Day 23 | Build: Store conversation history in ChromaDB | Test retrieval | Embeddings | ☐
Jan 24 | Day 24 | Build: Semantic search over your documents | Experiment with similarity | Vector Search | ☐
Jan 25 | Day 25 | Build: Chat with PDF documents | Add: PyPDF loader | RAG (Retrieval Augmented Generation) | ☐
Jan 26 | Day 26 | Build: Create a personal knowledge base assistant | Test with your own notes | Knowledge Management | ☐
Jan 27 | Day 27 | Build: Add source tracking to retrievals | Improve citation accuracy | Metadata | ☐
Jan 28 | Day 28 | MILESTONE: Document QA Agent - Portfolio Project #1 | Deploy on GitHub with demo | Git, README | ☐
🛠️ MONTH 2: TOOL-USING AGENTS (February)
Week 5: Custom Tools
Jan 29 | Day 29 | Build: Weather checking tool using API | Setup: OpenWeatherMap API | Tool Creation | ☐
Jan 30 | Day 30 | Build: Stock price lookup tool | Use: yfinance library | Financial Data | ☐
Jan 31 | Day 31 | Build: Agent that uses both tools automatically | Read: Tool selection logic | Multi-Tool Agents | ☐
Feb 01 | Day 32 | Build: Email sending tool (Gmail API) | Setup: Gmail credentials | Email Automation | ☐
Feb 02 | Day 33 | Build: Calendar checking tool | Integrate: Google Calendar API | Calendar Integration | ☐
Feb 03 | Day 34 | Build: Personal assistant agent (weather + calendar + email) | Test real scenarios | Orchestration | ☐
Feb 04 | Day 35 | Build: Add error handling and retries | Learn: Robust tool execution | Error Management | ☐
Week 6: Web Automation Agent
Feb 05 | Day 36 | Build: Install Playwright, create browser automation | Learn: Headless browsers | Web Automation | ☐
Feb 06 | Day 37 | Build: Form filling agent | Test on real websites | DOM Manipulation | ☐
Feb 07 | Day 38 | Build: Web scraping with intelligent extraction | Add: BeautifulSoup | Web Scraping | ☐
Feb 08 | Day 39 | Build: E-commerce price tracker | Track Amazon prices | Practical Automation | ☐
Feb 09 | Day 40 | Build: Automated job application assistant | Test with job boards | Form Automation | ☐
Feb 10 | Day 41 | Build: Social media post scheduler | Add: Twitter API | Social Automation | ☐
Feb 11 | Day 42 | MILESTONE: Web Automation Agent - Portfolio Project #2 | GitHub + video demo | Documentation | ☐
Week 7: Code Execution Agent
Feb 12 | Day 43 | Build: Python code executor (sandbox) | Setup: safe code execution | Code Execution | ☐
Feb 13 | Day 44 | Build: Data analysis agent (reads CSV, generates insights) | Test with real datasets | Data Analysis | ☐
Feb 14 | Day 45 | Build: Chart generation agent (matplotlib) | Create visualizations | Data Viz | ☐
Feb 15 | Day 46 | Build: Automated testing agent | Write test cases with Claude | Testing | ☐
Feb 16 | Day 47 | Build: Code review agent | Analyze your own code | Code Quality | ☐
Feb 17 | Day 48 | Build: Bug fixing assistant | Debug real code | Debugging | ☐
Feb 18 | Day 49 | Build: SQL query generator and executor | Add: SQLite database | Database Integration | ☐
Week 8: Planning Agents
Feb 19 | Day 50 | Build: Task decomposition agent | Break complex tasks into steps | Planning | ☐
Feb 20 | Day 51 | Build: Multi-step planner with validation | Add: step verification | Hierarchical Planning | ☐
Feb 21 | Day 52 | Build: Goal-oriented agent (travel planner) | Plan full itineraries | Goal Setting | ☐
Feb 22 | Day 53 | Build: Budget tracking agent | Track expenses automatically | Financial Planning | ☐
Feb 23 | Day 54 | Build: Meal planning and recipe agent | Generate shopping lists | Daily Life Automation | ☐
Feb 24 | Day 55 | Build: Study schedule optimizer | Create learning plans | Education | ☐
Feb 25 | Day 56 | MILESTONE: Planning Agent System - Portfolio Project #3 | Full documentation | Polish | ☐
🧠 MONTH 3: ADVANCED PATTERNS (March)
Week 9: Multi-Agent Systems
Feb 26 | Day 57 | Build: Install CrewAI framework | Read: Multi-agent concepts | CrewAI | ☐
Feb 27 | Day 58 | Build: Two-agent system (researcher + writer) | Define roles and goals | Agent Roles | ☐
Feb 28 | Day 59 | Build: Three-agent content creation team | Add: editor agent | Collaboration | ☐
Mar 01 | Day 60 | Build: Debate agent system (pro/con arguments) | Test controversial topics | Reasoning | ☐
Mar 02 | Day 61 | Build: Code review team (analyzer + fixer + tester) | Review real codebases | Software Development | ☐
Mar 03 | Day 62 | Build: Customer support agent system | Handle different query types | Customer Service | ☐
Mar 04 | Day 63 | Build: Autonomous task delegation system | Agent assigns work to others | Orchestration | ☐
Week 10: Advanced RAG
Mar 05 | Day 64 | Build: Multi-document RAG system | Index 100+ documents | Scalable RAG | ☐
Mar 06 | Day 65 | Build: Hybrid search (keyword + semantic) | Combine both methods | Search Optimization | ☐
Mar 07 | Day 66 | Build: Query rewriting for better retrieval | Improve search quality | Query Engineering | ☐
Mar 08 | Day 67 | Build: Re-ranking system for results | Add: Cohere reranker | Result Optimization | ☐
Mar 09 | Day 68 | Build: Conversational RAG with memory | Track conversation context | Contextual RAG | ☐
Mar 10 | Day 69 | Build: Citation and source tracking | Show exact sources | Transparency | ☐
Mar 11 | Day 70 | Build: Domain-specific RAG (legal/medical/finance) | Specialize your system | Domain Adaptation | ☐
Week 11: Autonomous Agents
Mar 12 | Day 71 | Build: Self-improving agent with feedback loops | Agent learns from mistakes | Self-Improvement | ☐
Mar 13 | Day 72 | Build: Goal-driven agent (AutoGPT style) | Set goals, let it work | Autonomy | ☐
Mar 14 | Day 73 | Build: Resource-constrained agent (budget limits) | Manage API costs | Resource Management | ☐
Mar 15 | Day 74 | Build: Multi-modal agent (text + images) | Add: image analysis | Multi-Modal | ☐
Mar 16 | Day 75 | Build: Real-time monitoring agent | Track metrics continuously | Monitoring | ☐
Mar 17 | Day 76 | Build: Automated report generation system | Daily/weekly reports | Reporting | ☐
Mar 18 | Day 77 | MILESTONE: Autonomous Agent - Portfolio Project #4 | Most impressive project yet | Showcase | ☐
Week 12: Production Ready
Mar 19 | Day 78 | Build: Add logging and monitoring | Track all agent actions | Observability | ☐
Mar 20 | Day 79 | Build: Error recovery and fallback systems | Handle failures gracefully | Reliability | ☐
Mar 21 | Day 80 | Build: Rate limiting and cost control | Prevent runaway costs | Cost Management | ☐
Mar 22 | Day 81 | Build: User authentication system | Add: login/permissions | Security | ☐
Mar 23 | Day 82 | Build: API endpoint for your agent | Use: FastAPI | API Development | ☐
Mar 24 | Day 83 | Build: Basic web interface | Use: Streamlit | UI/UX | ☐
Mar 25 | Day 84 | Build: Deployment script (Docker) | Containerize your app | DevOps | ☐
💰 MONTH 4: SIDE HUSTLE LAUNCH (April)
Week 13: Market Research
Mar 26 | Day 85 | Build: Competitive analysis agent | Research similar products | Market Analysis | ☐
Mar 27 | Day 86 | Build: Pricing optimization tool | Analyze market rates | Pricing Strategy | ☐
Mar 28 | Day 87 | Build: Target customer identifier | Find ideal clients | Customer Research | ☐
Mar 29 | Day 88 | Build: Feature prioritization system | Decide what to build | Product Strategy | ☐
Mar 30 | Day 89 | Build: Landing page generator | Create with Claude | Marketing | ☐
Mar 31 | Day 90 | Build: Cold email outreach agent | Personalized emails | Sales | ☐
Apr 01 | Day 91 | Build: Demo video creation plan | Script and storyboard | Content Marketing | ☐
Week 14: Product Development
Apr 02 | Day 92 | Build: Choose your niche (freelance tool, productize) | Validate with potential customers | Product Selection | ☐
Apr 03 | Day 93 | Build: MVP of your product | Simplest version that works | MVP Development | ☐
Apr 04 | Day 94 | Build: Customer onboarding system | Make it easy to start | UX | ☐
Apr 05 | Day 95 | Build: Feedback collection mechanism | Get user input | Product Feedback | ☐
Apr 06 | Day 96 | Build: Payment integration (Stripe) | Setup: Stripe account | Monetization | ☐
Apr 07 | Day 97 | Build: Usage tracking and analytics | Monitor product usage | Analytics | ☐
Apr 08 | Day 98 | Build: Documentation and tutorials | Help users succeed | Documentation | ☐
Week 15: Marketing & Sales
Apr 09 | Day 99 | Build: Personal brand content agent | Generate LinkedIn posts | Personal Branding | ☐
Apr 10 | Day 100 | Build: Case study generator | Document your work | Social Proof | ☐
Apr 11 | Day 101 | Build: Cold outreach campaign | Contact 50 potential clients | Outreach | ☐
Apr 12 | Day 102 | Build: SEO optimization for your site | Optimize content | SEO | ☐
Apr 13 | Day 103 | Build: Email nurture sequence | Automated follow-ups | Email Marketing | ☐
Apr 14 | Day 104 | Build: Affiliate program (if applicable) | Incentivize referrals | Growth | ☐
Apr 15 | Day 105 | MILESTONE: First paying customer or contract | Launch and iterate | Revenue | ☐
Week 16: Scale & Iterate
Apr 16 | Day 106 | Build: Customer success agent | Help customers get value | Retention | ☐
Apr 17 | Day 107 | Build: Automated invoicing and reminders | Handle finances | Business Ops | ☐
Apr 18 | Day 108 | Build: Testimonial collection system | Gather social proof | Marketing | ☐
Apr 19 | Day 109 | Build: Referral program automation | Grow through referrals | Growth | ☐
Apr 20 | Day 110 | Build: Portfolio website update | Showcase everything | Personal Brand | ☐
Apr 21 | Day 111 | Build: Content marketing engine | Regular blog/video output | Content | ☐
Apr 22 | Day 112 | FINAL: You have a side hustle generating income! | Celebrate and plan next steps | Success | ☐

## Quick Reference
📋 QUICK REFERENCE GUIDE
⏱️ Time Commitment | 2 hours daily (14 hours/week = 56 hours/month)
🎯 Strategy | 80% Building, 20% Learning - Ship working code every day
📦 Essential Tools to Install
Week 1 | anthropic, openai, python-dotenv
Week 2 | google-search-results (SerpAPI)
Week 3 | langchain, langchain-anthropic, langchain-community
Week 4 | chromadb, pypdf, sentence-transformers
Week 6 | playwright, beautifulsoup4, selenium
Week 9 | crewai, autogen
Week 14 | fastapi, streamlit, stripe
🎓 Free Learning Resources
• Anthropic Documentation: docs.anthropic.com
• LangChain Docs: python.langchain.com
• DeepLearning.AI: Free courses on AI agents
• YouTube: Channels like Greg Kamradt, Matt Williams
💡 Side Hustle Ideas
Freelance Services | • Custom chatbots for small businesses ($500-2000)
• Document automation agents ($300-1000)
• Social media content generators ($200-500/month)
SaaS Products | • Email automation tool ($29-99/month)
• Meeting notes AI assistant ($19-49/month)
• Research assistant for students ($9-19/month)
🚀 Success Metrics by Month
End of Month 1 | ✓ 1 working agent on GitHub + basic portfolio
End of Month 2 | ✓ 3 portfolio projects + understanding of tool use
End of Month 3 | ✓ 4-5 advanced projects + production-ready skills
End of Month 4 | ✓ First paying customer OR launched product
⚠️ Common Mistakes to Avoid
• Tutorial hell - Build immediately, don't watch 10 videos first
• Perfect code - Ship messy code daily, refactor later
• Building everything - Focus on 1 niche in Month 4
• Ignoring cost - Always monitor API usage and set limits
• No documentation - Write README as you build